#### MATH3004 Industrial Project – Progress Report, 2026 Semester 2.

PLEASE SUBMIT THE PROGRESS REPORT TO THE UNIT CO-ORDINATOR BY 5PM FRIDAY 25 SEPTEMBER.

Project Title:  ​Comparative Prediction Accuracy of Statistical, Machine Learning and Deep Learning Approaches in Forecasting Daily Perth Fuel Prices

| Week starting from | Tasks (Corresponding to the timeline plan) | Score (for supervisor(s) to rate) |  |  |
| --- | --- | --- | --- | --- |
|  |  | 1-2 Not meet expectations | 3-4 Meets expectations | 5 Exceeds expectations |
| 3 August | Literature review; environment setup; data inspection; agreed on train/val/test split with team |  |  |  |
| 10 August | Exploratory data analysis; verified Wednesday spike; built initial OLS with 27 features |  |  |  |
| 24 August | Diagnosed multicollinearity (condition number 1.59e16); pruned to 11 features; re-fitted OLS |  |  |  |
| 31 August | Evaluated OLS on validation and test; compared against naive baseline; documented R² divergence |  |  |  |
| 7 Sept | Regime decomposition: normal/shock/post-shock; identified shock-period boundary condition |  |  |  |
| 14 Sept | Generated final figures; drafted OLS report section; shared frozen splits with teammates |  |  |  |
| 21 Sept | Handoff complete, ready for team comparison phase |  |  |  |
| Total marks out of 35 |  |  |  |  |

Student:	____Bao Minh TRAN  ___________________________									(					)

Approved:	___Honglei Xu____________________________

(					)
										     Project Supervisor

Date:		_______________________________